## Doc_Weekly Status_Jan2014
|  | Meeting Invite & Agenda | Meeting Invite & Agenda | Meeting Invite & Agenda | Meeting Invite & Agenda
Venue | Sensys Conference Room | Engineering Head Office | Engineering Head Office
Date | 41642 | 2014-01-21 | 2014-01-28
Time | 0.97917 | 11:30 | 11:30
Duration | 1 hour | 30 minutes | 30 minutes
Recurrence | Single | Weekly | Weekly
Agenda | FS Walkthrough for RT Notifications | Weekly Status/Dashboard/KPI: | Weekly Status/Dashboard/KPI:
|  | 1. Documentation Dashboard Review | 1. Documentation Dashboard Review
|  | 2. Project Schedule Review on Project Server | 2. Project Schedule Review on Project Server
|  | 3. Update Meeting Agenda Items | 3. Update Meeting Agenda Items
Add more rows above (if required).
Meeting Minutes
Sr. No. | Action Items | Owner Name | Priority (Emergency Square/Emergency/High/Medium/Low/Very Low) | Status (Open/In-progress/ On-hold/Completed/Closed) | Notes Taken On Date | Expected Start Date | Due Date | Expected End Date | Comments | Author
1 | Documentation needs an urgent upgrade to latest Robohelp release for viewing help on IE 11. For the resolution, this problem should be reported to Management through a suggestive email. | Documentation (Sadaf Mufti) | High | Open | 2014-01-21
2 | Email to SCM: Establishing best practices for incorporating updated help content in Product Patches | Documentation (Sadaf Mufti) | High | Open | 2014-01-21
Add more rows above (if required).
Sr. No. | Important Notes (Discussion Points/Decisions/Guidelines) | Contributor Name | Owner Name | Notes Taken On Date
1 | Product Documentation for all roadmap items of IMAX 4.6.4 has been delivered including major Bug Fixes. | Sadaf Mufti | Documentation | 2014-01-21
2 | Robohelp 8 generated Webhelp output is having issues with IE 11 browser that imposes a serious threat to the management's plan of bringing IE 11 compatibility in IntelliMAX. | Sadaf Mufti, Rehan Bin Khalid | Documentation | 2014-01-21
3 | Product Patches will now be released with updated Documentation since webhelp size limitation has been overcome by replacing only the updated HTML/JPEG file instead of whole web help. | Sadaf Mufti | Documentation | 2014-01-21
Add more rows above (if required).
Appendix A: (if required)
1
2
3
4
5
Add more rows above (if required).
Attendance Log
Date |  | 2014-01-21 | 2014-01-28
Start Time |  | 12:20
End Time |  | 12:50
Duration |  | 0.020833 | 0
Sr. No. | Attendees (Names/Designations/Roles) | Attendance 1 | Attendance 2 |  | Joining Time
1 | Muhammad Usman | Present
2 | Sheraz Pervaiz | Absent (Informed, 1st Half Leave)
3 | Sadaf Mufti | Present
4 | Rehan Bin Khalid | Present
Add more rows above (if required).
Formulas:
Meeting Invite & Agenda = [Meeting Invite & Agenda, row above]-C31
Meeting Invite & Agenda = [Meeting Invite & Agenda, row above]-D31
Note on A6: Author: (Single/Daily/Weekly/Fortnightly/Monthly/Quarterly/Yearly)
Note on B16: Author: